## Sheet1
Dee Project Manager
Project Name
Project Manager
ID | Phase | Lesson | Impact | Impact Type | Recommended Action | Date of Entry
1 | Planning | Software integration was more complex than anticipated | 2 weeks' delay | Schedule | Involve software engineers in project planning phase | 2023-06-01
2 | Execution | Client communication was not frequent enough | Resulted in client dissatisfaction and rework | Quality/Customer Satisfaction | Implement weekly status updates for all clients | 2023-06-15
3 | Closure | Final documentation took longer than expected | Delayed project closure by 1 week | Schedule | Allocate more time for final documentation in future project plans | 2023-07-10
4 | Initiation | Stakeholder expectations were not clearly outlined | Misalignment in project objectives | Scope | Ensure clear documentation of stakeholder expectations at project initiation | 2023-07-25